NHS Devon Integrated Care Board

Board Assurance Framework

| Date of committee | Date report produced |
| --- | --- |
| 15 March 2023 | 7 March 2023 |

| Author(s) |  | Report approved by |  |
| --- | --- | --- | --- |
| Name and title: | Ann Cooper, Interim Strategic Governance Adviser | Name and title: | Andrew Millward, Chief Communications and Corporate Affairs Officer, NHS Devon |
| Phone: |  | Date: | 7 March 2023 |
| Email: | Ann.cooper19@nhs.net |  |  |

If this paper needs to be presented at a private meeting, please state why and mark as CONFIDENTIAL:

Executive summary (250 words max) – high level overview of the content of the report and the reasons why it is being presented

This report provides Board members with a report on the high-level strategic risks that pose a threat to the achievement of the NHS Devon (the ICB) strategic objectives. Principal assurance committee nominated for each risk. Board members are invited to consider: - the updated BAF risks, and the assurances provided against each one; - changes to the wording for strategic objective 6; - the risk description for strategic objective ; and - the risk description for strategic objective 6.

Committees that have previously discussed/agreed the report, and outcomes of that discussion

Executive Team 7 March 2023 – agreed Quality Committee 1 March 2023 - agreed Primary Care Commissioning Committee – changes made to strategic objective 6 and the related risk description.

Key recommendations and actions requested – please be explicit on what you are asking the committee/board to do

Board members are asked to AGREE: - the updated iteration of the Board Assurance Framework; and - the proposed changes to strategic objective 6 and the risk descriptions for objectives 1 and 6.

| Impact on NHS Devon objectives |  |
| --- | --- |
| Objective | Impact |
| Improve population health | All |
| Improve services and reduced unwarranted variation |  |
| Make more efficient use of our resources |  |
| Develop our culture and how we operate |  |

| Outline the implications of matters covered in this report for the following areas (if none, please state) |  |
| --- | --- |
| Area |  |
| Quality of services | The BAF in itself does not present any quality or safety implications. It captures and reports the strategic risks relating to population health outcomes and patient experience in the Devon ICS. |
| Health inequalities | The results of any EHIA will inform mitigating actions in the BAF moving forward. |
| Workforce | None |
| Resources and finance | The BAF in itself does not present any financial implications. It captures and reports the strategic financial risks faced by NHS Devon. |
| Legal | Sound risk management systems are an essential component of internal control processes. NHS organisations are required to sign an annual governance statement to provide reasonable assurance that they have been properly informed about the totality of their risks and can evidence that they have identified the organisational objectives and managed the principal risks to them. |
| Digital and Data | None |
| Involvement, Engagement and consultation | None |

Board Assurance Framework:

How well does the new NHS Devon BAF mitigate the key risks to the achievement of the organisation’s strategic objectives and what is the Board’s appetite for risk?

Introduction

An organisation’s Board Assurance Framework (BAF) brings together in one place all the relevant information on risks to the Board’s strategic objectives.

Current Risk Position

|  |  |  |  |  |  |  |  | Historical and Current Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Title |  | Strategic Objective |  | Monitoring Committee |  | Inherent Risk Score |  | Jan’23 | Feb’23 | Mar’23 | Change | Target | Risk Appetite |  | Last Reviewed |  |
| Improve Population Health |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Anchor |  | 1 |  | Quality |  | 16 |  |  | 16 | 16 | No change | 8 | Seek |  | Feb 23 |  |
| Inequalities |  | 2 |  | Quality |  | 16 |  |  | 16 | 16 | No change | 8 | Seek |  | Feb 23 |  |
| Prevention |  | 3 |  | Quality |  | 16 |  | 12 | 12 | 12 | No change | 8 | Open |  | Feb 23 |  |
| Improve services and reduce unwarranted variation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recovery |  | 4 & 5 |  | Finance |  | 16 |  | 9 | 9 | 9 | No change | 6 | Open |  | Feb 23 |  |
| Primary Care |  | 6 |  | Primary care |  | 16 |  |  | 16 | 16 | No change | 8 | Seek |  | Feb 23 |  |
| MHLD |  | 7 |  | Finance |  | 20 |  |  | 15 | 16 | No change | 10 | Open |  | Feb 23 |  |
| Community |  | 8 |  | Primary Care |  | 20 |  |  | 16 | 16 | No change | 8 | Seek |  | Feb 23 |  |
| Make more efficient use of resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finance |  | 9 |  | Finance |  | 20 |  | 16 | 16 | 16 | No change | 8 | Open |  | Feb 23 |  |
| Workforce |  | 10 |  | People & Culture |  | 16 |  | 12 | 12 | 12 | No change | 6 | Open |  | Feb 23 |  |
| Digital |  | 11 |  | Finance |  | 16 |  |  | 12 | 12 | No change | 8 | Seek |  | Feb 23 |  |
| Green Plan |  | 12 |  | Finance |  | 16 |  |  | 12 | 12 | No change | 8 | Seek |  | Feb 23 |  |
| Develop our culture and how we operate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integration |  | 13 & 14 |  | ICS exec |  | 16 |  | 16 | 16 | 16 | No change | 6 | Seek |  | Feb 23 |  |

The details for each risk are attached at the Annex A and the scoring methodology in Annex B of this report.

Issues to highlight to the Board

There have been adjustments made to the wording of two strategic objectives.

The first is objective number 1 Work in partnership with community and ‘anchor’ organisations to address the social determinants of health. Previously it had included reference to education and police, which have now been removed.

The second is objective 6 which has been updated following the BAF review at the Primary Care Commissioning Committee in February 2023. The previous objective was:

- Improve the capacity of primary care with particular attention to challenged areas such as Plymouth.

The proposed wording for objective 6 is:

Maintain and enhance the capacity and resilience of Primary Care providers to improve patient outcomes through prevention, long term condition management and appropriate on the day demand, with particular attention to challenged areas.

The risk description now reads as follows:

If the ICB does not support the post-Covid recovery and transformation of general medical, dental, pharmaceutical and optical practice then Devon will not have adequate Primary Care Services.  The consequence will be increased population morbidity, increased health inequalities and increased pressure across other parts of the health and care system.

Conclusion

Board members are invited to consider the proposed changes to strategic objective 6 and the risk descriptions for objectives 1 and 6.

| Improve population health Corporate Objective: (1) Work in partnership with community and ‘anchor’ organisations to address the social determinants of health. |  |  |  |  |  |  | Director Lead: Nigel Acheson |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk If the Anchor Organisation programme of work is not part of a more strategic plan then there will be a lack of focus to address the social determinants of health. As a consequence the partner and community organisations will become disengaged and the ICB will fail to achieve this objective. |  |  |  |  |  |  | Principal Assurance Committee: Quality Committee |  |  |  |  |  |
|  |  |  |  |  |  |  | Devon Challenge: 3: Complex patterns of urban, rural and coastal deprivation 4: Housing Quality and affordability 6: Access to services, including socio-economic and cultural barriers 11: Poor mental health and wellbeing, social isolation and loneliness ICS Strategic Goal: Helping the NHS support broader social and economic development |  |  |  |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target |  | Risk Appetite: Seek |  |  |  |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 |  | 8 |  |  |  |  |  |  |  |
| Risk score: Feb 23 | 4 | 4 |  | 16 |  |  |  |  |  |  |  |  |  |
| Key update on actions See mitigating actions |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |  |  |  |
| Anchor Organisation work programme |  |  |  |  |  |  | Reporting to Executive Strategy and Transformation Group |  |  |  |  |  |
| articulate the overarching vision and ambitions of the Anchor work. |  |  |  |  |  |  | Reporting to Integrated Care Partnerships |  |  |  |  |  |
|  |  |  |  |  |  |  | Reporting to the Health Inequalities and Prevention Steering Group |  |  |  |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |  |  |  |
| Work on Anchor Organisations not embedded across ICB and ICS |  |  |  |  |  |  | Formal governance arrangements not in place and no formal route to the NHS Devon Board. |  |  |  |  |  |
| Workforce – programme support identified within the Population Health Team |  |  |  |  |  |  |  |  |  |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  |  | Action Status |  | Planned Completion Date |  |
| Alignment of Anchor Organisation work programme with Joint Forward Plan |  |  |  |  |  |  |  |  |  |  | March 23 |  |
| Mapping work to address social determinants |  |  |  |  |  |  |  |  |  |  | Sept 23 |  |
| Co-ordination of LCP work on social determinants to share good practice. |  |  |  |  |  |  |  |  |  |  | June 23 |  |  |  |
| Connect ICB/ICS ambitions with the LEP and AHSN activity to develop common approach |  |  |  |  |  |  |  |  |  |  | March 23 |  |  |  |
| Improve Population Health Corporate Objective: (2) Reduce health inequalities (HI) through public health and mental health support. |  |  |  |  |  |  | Director Lead: Nigel Acheson |  |  |  |  |  |
| Risk: If there is insufficient capacity and capability in the ICB to undertake the enabling work with partners (Public Health and locality teams) then the ICB will not be able to articulate the programmes of work needed, and associated governance arrangements, to support the objective of reducing health inequalities. The consequence will be that health inequalities will continue across Devon and worsen in some areas. |  |  |  |  |  |  | Principal Assurance Committee: Quality Committee |  |  |  |  |  |
|  |  |  |  |  |  |  | Devon Challenge: 8: Earlier onset of health problems in more deprived areas 11: Poor mental health and wellbeing, social isolation and loneliness. ICS Strategic Goal: Population heath and prevention will be everybody's responsibility and inform everything we do. The focus will be on the top five modifiable risk factors for early death early and disability. |  |  |  |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target |  | Risk Appetite: Seek |  |  |  |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 |  | 8 |  |  |  |  |  |  |  |
| Risk score: Feb 23 | 4 | 4 |  | 16 |  |  |  |  |  |  |  |  |  |
| Key update on actions ICB continues to work with partners through existing steering and programme groups to align work across the localities. Recruitment ongoing to create a team to support the health inequalities and prevention programme plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |  |  |  |
| Population Health Team to provide support, advice and capacity |  |  |  |  |  |  | Reporting to Executive Strategy and Transformation Group |  |  |  |  |  |
| Health Inequalities and Prevention Steering Group |  |  |  |  |  |  |  |  |  |  |  |  |
| Health Inequalities and Prevention Programme Plan |  |  |  |  |  |  |  |  |  |  |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |  |  |  |
| Workforce: gaps in project management support and vacancies in Population Health Team. |  |  |  |  |  |  | Formal governance arrangements not in place and no formal route to the ICB Board. |  |  |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  |  |  | Action Status |  | Planned Completion Date |
| Recruitment and induction of team |  |  |  |  |  |  |  |  |  |  |  | Ongoing |
| Refresh of HI and prevention Steering Group |  |  |  |  |  |  |  |  |  |  |  | March 2023 |
| Refresh of HI and prevention plan |  |  |  |  |  |  |  |  |  |  |  | April 2023 |  |  |
| Establish formal governance to oversee Health Inequalities and Prevention Programme Plan |  |  |  |  |  |  |  |  |  |  |  | April 2023 |  |  |

| Improve population health: Corporate Objective: (3) Enable a greater shift from treatment to prevention |  |  |  |  |  |  | Director Lead: Nigel Acheson |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk If the ICB is not proactive in its approach and priorities around population health management and prevention then it will not successfully drive the shift to prevention. This will impact on the system’s ability to successfully target interventions at those groups most at risk, prevent ill-health and address health inequalities. |  |  |  |  |  |  | Principal Assurance Committee: Quality Committee |  |  |
|  |  |  |  |  |  |  | Devon Challenge 7: Poor health outcomes caused by modifiable behaviours and earlier onset of health problems in more deprived areas. ICS Strategic Goal: improving outcomes in population health and healthcare Population heath and prevention will be everybody's responsibility and inform everything we do. The focus will be on the top five modifiable risk factors for early death early and disability. People in Devon will be supported to stay well at home, through preventative, pro-active and personalised care. The focus will be on the five main causes of early death and disability. |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target | Appetite: Open Willing to consider all potential delivery options while also providing acceptable levels of service provision. |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 |  | 8 |  |  |  |
| Risk score: Feb 23 | 3 | 4 |  | 12 |  |  |  |  |  |
| Key update on actions for Feb 2023 The Integrated Care Partnership (ICP; One Devon) has agreed an Integrated Care (IC) Strategy and Dr. Lincoln Sargeant (Devon SRO for Health Inequalities and Prevention, and Director of Public Health for Torbay) co-chairs the working group. Previously seen as a “public health function” there is now a clear recognition that prevention needs to be embedded in all planning for healthcare. A programme of work has been established to address these priorities led by Lincoln Sargeant as the SRO. It is important that this work remains a high priority. The establishment of the One Devon Dataset, a linked dataset at an individual and community level bringing together data on health, care, public health, population and community characteristics will identify cohorts and allow interventions to be planned which focus on health determinants and health inequalities. |  |  |  |  |  |  |  |  |  |
| Key Controls expected |  |  |  |  | In place |  | Key Assurances: |  |  |
| Nominate SRO |  |  |  |  |  |  | Reducing & Mitigating Against Health Inequalities in Planned Care paper to Public Board 18 January 2023 showing progress against work plan for planned care. |  |  |
| Population health inequality considerations are taken into account when NHS Devon makes decisions about the use of resources to deliver its objectives. |  |  |  |  |  |  | Policy to ensure that health inequalities are addressed in NHS Devon decision making |  |  |
| Gaps in controls |  |  |  |  |  |  | Gaps in Assurances |  |  |
| Structure of public health and population health management teams in ICB not finalised |  |  |  |  |  |  | Assessment of public health and population health management capacity in progress |  |  |
| ICB evaluation capability and capacity (simple logic models, development of measurement frameworks etc.) not established |  |  |  |  |  |  | Governance of monitoring in relation to population health management and prevention outcomes not finalised |  |  |
| Programme yet to be agreed on the management of diabetes and cardiovascular disease prevention. |  |  |  |  |  |  |  |  |  |
| Mitigating Actions: Priority order |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| - Creating a programmes of work on cardiovascular disease prevention and management of diabetes. |  |  |  |  |  |  |  |  | May 2023 |
| - One Devon Dataset (see digital strategic risk) |  |  |  |  |  |  |  |  | tbc |
| - Formalise reporting on population health management – baseline reporting to be agreed. |  |  |  |  |  |  |  |  | April 2023 |
| - Review use of EHIA and assess further development requirements |  |  |  |  |  |  |  |  | May 2023 |

| Improve services and reduce unwarranted variation Corporate Objective: (4) Deliver safe and effective urgent and emergency care services that better meet people’s needs (5) Reduce the number of people waiting for elective care – with a specific short-term focus on 104-week waits. |  |  |  |  |  |  | Director Leads: SRO Anthony Fitzgerald – delivery and improvement |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk If the system does not have robust recovery plans, that are continually monitored for impact, then the ICB will continually fail to ensure timely access to both elective and unplanned care. This will result in poor patient experience, failure to ensure the best possible physical and mental health outcomes and resulting quality of life; generating inappropriate and inefficient use of resource in primary care and a and loss of confidence from the community and regulators. |  |  |  |  |  |  | Principal Assurance Committee: Finance Committee |  |  |
|  |  |  |  |  |  |  | Devon Challenge 12: Pressure on health and care services (especially unplanned care) ICS Strategic Goal: People in Devon will know how to access the right service first time and navigate the services they need across health and care, improving personal experience and service productivity and efficiency. |  |  |
|  | Likelihood | Impact | Move | Risk Score | Target |  | Appetite: Open |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 | 6 |  |  |  |  |
| Risk score Mar 23 | 3 | 3 |  | 9 |  |  |  |  |  |
| Key update on actions for Feb/Mar 2023 (a) System Urgent Care improvement focusing on: 1. Out of Hospital Improvement - Creation of additional out of hospital capacity through operational plan investments for 23/24 focussing on increased community capacity via agreed locality plans - Delivery of the Western ambulance improvement programme - Creation of additional mental health capacity - Enhanced IUC service offer and performance - Enhance UCR fallers service to reduce ambulance conveyance - Increase capacity in community urgent care services - Prevent avoidable admissions through work with care homes and GP practices. |  |  |  |  |  | (b) Elective care recovery focusing on: - delivering zero 104ww for all specialties by 31st March 23 and maintaining this position in 23/24 - Ensure all patients waiting > 78ww have had a clinical review or clinical validation within 12 weeks of last review - All 78 week non-admitted patients to have had a 1st outpatient appointment by 31st March 23. - Review all 65ww and 78 ww cohort patients to ensure no EBI procedures are planned, if any identified clinical review must identify if DTA can be reconsidered - Implement the interim operational guidance on managing patient choice & active monitoring to best effect - Review and Improve Length of Stay for all specialties to improve flow and enable protection of agreed elective bed |  |  |  |
| 2. In Hospital Improvement - Increase SDEC usage - Enhance MTU model - Meet 50% of initial assessments completed within 15 mins - Meet 80% of patients discharged by 17:00hrs - Increased virtual ward capacity quantified and delivered through the 23/24 operating plan and reflected in performance trajectories - Maximise boarding opportunities to minimise ED occupancy - Develop non elective LOS improvement trajectories - Increase in weekend discharge – insourcing of additional medical staffing and embed ward standard processes - Delivery of the transformation workstreams including low risk chest pain, abdominal pain, and paediatric assessment |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |
| Planned Care Board |  |  |  |  |  |  | Monthly IQPR reports to the Board |  |  |
| Devon Strategic Oversight Group for U&EC (established Nov 2022) Now being repurposed as the Devon Urgent Care Board |  |  |  |  |  |  | Elective Recovery Fund and Targeted Innovation Funding received. |  |  |
|  |  |  |  |  |  |  | Realignment of plans |  |  |
| U&EC Programme to support creation of the right conditions for success – enabling effective navigation of UEC care through 111. |  |  |  |  |  |  | Realignment of diagnostics |  |  |
| National weekly Tier 1 meetings in place |  |  |  |  |  |  | Western Recovery Plan |  |  |
| System Quality Group |  |  |  |  |  |  | Elective recovery plan |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |
| System wide Urgent and Emergency Care Strategy not signed off. |  |  |  |  |  |  | NHS Devon missing key performance targets No high-level summary on risks and issues on the IQPR |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| Urgent Care Boards to meet more regularly with clinical Chairs. |  |  |  |  |  |  |  |  | Starting from Mar 23 |
| Audit of elective care serious incidents is being undertaken by the ICB to ascertain the level of harm specifically due to long waits. Providers have also been asked to share their data on harm, including lower-level incidents and complaints. |  |  |  |  |  |  |  |  |  |
| Develop actions towards the 8 objectives set out in the Winter Plan to assist the SDIG allocation of resources for winter and in response to the Ambulance Handover Plan for Plymouth and the Prime Minister’s 100-day discharge plan |  |  |  |  |  |  |  |  |  |

| Improve Services and reduce unwarranted variation Corporate Objective : (6) Maintain and enhance the capacity and resilience of Primary Care providers to improve patient outcomes through prevention, long term condition management and appropriate on the day demand, with particular attention to challenged areas. |  |  |  |  |  |  | Director Lead: Jo Turl |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk: If the ICB does not support the post-Covid recovery and transformation of general medical, dental, pharmaceutical and optical practice then Devon will not have adequate Primary Care Services. The consequence will be increased population morbidity, increased health inequalities and increased pressure across other parts of the health and care system. |  |  |  |  |  |  | Principal Assurance Committee: Primary Care Commissioning Transition Committee |  |  |  |
|  |  |  |  |  |  |  | Devon Challenge: 1: An ageing and growing population 3: Complex patterns of urban, rural and coastal deprivation 7: Poor health outcomes caused by modifiable behaviours 8: Earlier onset of health problems in more deprived areas ICS Strategic Goal: We will have a safe and sustainable health and care system. |  |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target |  | Risk Appetite: Seek |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 |  | 8 |  |  |  |  |
| Risk score: Feb 23 | 4 | 4 |  | 16 |  |  |  |  |  |  |
| Key update on actions General Practice Strategic Framework providing direction of travel for primary care. Localities to create local delivery plans. New ways of providing additional capacity with third party providers being tested in Plymouth and Torbay. PCNs to create plans for recruiting using the additional roles reimbursement fund. |  |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |  |
| Primary Care Commissioning Transition Committee |  |  |  |  |  |  | Monitoring reports in place showing General Practice dental, pharmaceutical and optical metrics – access, workforce etc |  |  |  |
| General Practice Strategic Framework |  |  |  |  |  |  |  |  |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |  |
| Resources – funding gap in general practice in capital allocation and winter monies; lack of funding for dental care |  |  |  |  |  |  | Demand and capacity – continuing high demand for primary care services alongside responding to the backlog in lower clinical priority, but essential work |  |  |  |
| System Constraints – operating within the national dental contract; still part of a hub system of commissioning. |  |  |  |  |  |  | Workforce – workforce shortages (across all allied professionals, nurses, GPs, dentists and community pharmacists) |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| Support and test different models of primary care provision to address practice sustainability for example, Plymouth integrated model with Livewell. |  |  |  |  |  |  |  |  |  | April 2023 |
| Support workforce initiatives that engage and retain high quality workforce in all Devon’s primary care services. |  |  |  |  |  |  |  |  |  | Ongoing |
| Support funding for a coherent primary care estates strategy. |  |  |  |  |  |  |  |  |  | Ongoing |

| Improve Services and reduce unwarranted variation Corporate Objective 7: Improve access to and outcomes for mental health (MH), learning disability (LD) and neurodiversity services. |  |  |  |  |  |  | Director Lead: Jo Turl |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk: If the ICB does not improve access to mental health, learning disability and neurodiversity services then patients will continue to experience significant waits for specialist care which means more people are likely to access healthcare when in crisis. Consequence will be a worsening in mental health conditions leading to poor health outcomes. This may lead to an increased population morbidity, increased health inequalities and increased pressure across other parts of the health and care system. |  |  |  |  |  |  | Principal Assurance Committee: Finance Committee |  |  |  |
|  |  |  |  |  |  |  | Devon Challenge: 7: Poor health outcomes caused by modifiable behaviours 12: Pressure on health and care services (especially unplanned care) caused by increasing long-term conditions, multi-morbidity and frailty. ICS Strategic Goal: People in Devon will be supported to stay well at home, through preventative, pro-active and personalised care. The focus will be on the five main causes of early death and disability. People in Devon will have access to the information and services they need, in a way that works for them, so everyone has an equal opportunity to be healthy and well. |  |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target |  | Risk Appetite: Open |  |  |  |
| Inherent Risk Score | 4 | 5 | No change | 20 |  | 10 |  |  |  |  |  |
| Risk score: Mar 23 | 3 | 5 |  | 15 |  |  |  |  |  |  |  |
| Key update on actions See mitigating actions. |  |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |  |
| Mental Health and LD Provider Collaborative monitoring performance and issues. |  |  |  |  |  |  | Performance data available to workstreams, oversight group and provider collaborative. |  |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps – what is not working |  |  |  |
| Workforce – difficulties in recruiting to specialist MH posts. For example, in ADHD services due to higher wages in private providers. |  |  |  |  |  |  | IQPR does not map all waiting times such as CAMHS |  |  |  |
| Resources – project support and reduction in commissioning personnel |  |  |  |  |  |  | Significant waiting times for patients trying to access Community Mental Health Teams; Autism and ADHD; Specialist Mental Health Services e.g eating disorders; and CAMHS. |  |  |  |
| Demand and capacity – high demand post COVID outstripping capacity |  |  |  |  |  |  | MH Care Records – eight-month gap in records as a consequence of a cyber-attack in 2022. Data only available post March 2023. Impact on receiving activity and waiting times data for CAMHS. |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| Operating Planning process run through MHLDN PC to agree system priorities |  |  |  |  |  |  |  |  |  | April 2023 |
| Prioritisation process to identify system priorities and alignment to available resources |  |  |  |  |  |  |  |  |  | May 2023 |

| Improve services and reduce unwarranted variation Corporate Objective: (8) Support and treat more people in their homes and communities to help them live healthily and independently. |  |  |  |  |  |  | Director Lead: Jo Turl |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk: If the ICB does not work with its partners to prioritise resources on how we support people and communities to stay healthy and live independently the consequence will be that we will always be in a state of crisis management, which will lead to poorer outcomes for the population. |  |  |  |  |  |  | Principal Assurance Committee: Finance / Primary Care Commissioning Transition |  |  |  |
|  |  |  |  |  |  |  | Devon Challenge: 1: An ageing and growing population ICS Strategic Goal: People in Devon will be supported to stay well at home, through preventative, pro-active and personalised care. The focus will be on the five main causes of early death and disability |  |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target |  | Risk Appetite: Seek |  |  |  |
| Inherent Risk Score | 5 | 4 | No change | 20 |  | 8 |  |  |  |  |  |
| Risk score: Mar 23 | 4 | 4 |  | 16 |  |  |  |  |  |  |  |
| Key update on actions See mitigating actions |  |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |  |
| Integrated Care Group regularly reviews workplan |  |  |  |  | Yes |  | Reporting Virtual Ward uptake through to SDIG |  |  |  |
| Publication of Community First framework |  |  |  |  | Yes |  |  |  |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |  |
| Community Provider Collaborative to be established |  |  |  |  |  |  | Limited community metrics through to Board via IQPR |  |  |  |
| Primary and Community Care Model programme to be agreed across system |  |  |  |  |  |  |  |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| Agree and implement the Community Provider Collaborative |  |  |  |  |  |  |  |  |  | May 2023 |
| Completion and implementation of EoL review recommendations |  |  |  |  |  |  |  |  |  | March 2024 |
| Implementation of Virtual Wards |  |  |  |  |  |  |  |  |  | March 2023 |  |  |
| Review of impact of Urgent Community Response |  |  |  |  |  |  |  |  |  | June 2023 |  |  |

| Make more efficient use of our resources Corporate Objective: (9) Move out of System Oversight framework (SOF4) – including delivery of a balanced system financial plan |  |  |  |  |  |  | Director Lead: Bill Shields |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk If the ICB fails to obtain commitment from all partners in the ICS to achieve financial balance. This will undermine our ability to move greater resource to prevention and our ability to exit the NHS England System Oversight Framework level 4 status (SOF4). |  |  |  |  |  |  | Principal Assurance Committee: Finance Committee |  |  |
|  |  |  |  |  |  |  | Devon Challenge 5: Economic Resilience ICS Strategic Goal: enhancing productivity and value for money - We will make the best use of our funds by maximising economies of scale and increasing cost effectiveness. |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target | Appetite: Open Our preference is for risk avoidance. However, if necessary we will take decisions where there is a low degree of inherent risk and the possibility of improved outcomes, and appropriate controls are in place. |  |  |
| Inherent Risk Score | 4 | 5 | No change | 20 |  | 8 |  |  |  |
| Risk score: Feb 23 | 4 | 4 |  | 16 |  |  |  |  |  |
| Key update on actions Update Feb 2023 The Finance Committee agreed in January 2023, based on month 09 financial performance, to move the forecast outturn positions for our providers and system to a deficit of £49.5m. Allocations for 23/24 were received at the end of December 2022, and the planning process for 2023/24 is progressing at pace. Give the financial position of the system, agreement has been reached to work up 4 scenarios in delivery of the of the initial submission due 23 February 2023. Chief Executives and Directors of Finance are working to agree the best scenario which will be used to inform financial, activity and workforce planning for the initial submission. There is broad recognition that it will be challenging to deliver both performance and financial balance, and the compromise plan will need to articulate the impact on these as well as our status in the System Oversight Framework (SOF). Further work on the plan will continue, working with NHS England, to work towards an overall agreed final plan at the end of March 23. The plan is unlikely to deliver an exit from SOF4. Board report in December 2022 to confirm m7 financial position with an outlook on end of year outturn: As at month 7 the Devon ICS is reporting year to date £20.9m deficit against a planned deficit of £15.9m – an adverse variance of £5m (M6 £4m). The reported forecast is a deficit of £18.2m which delivers to plan. At the planning stage net risks of £95.9m were identified to delivery of a break-even plan. At the end of month 7, this has improved by £39.4m and stands at £56.5m (£38.3m against plan) against an expectation of break-even. (M6 £61.5m) In addition to continuous drive to reduced CIP shortfall, the ICS is committed to delivering further mitigation through a Financial Recovery Plan, consisting of 10 workstreams. |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |
| Financial recovery plan |  |  |  |  |  |  | Financial Recovery Plan reported to Board 21 December 2022 |  |  |
| Newly appointed Executive Director of Finance |  |  |  |  |  |  | Finance Committee report re risks and mitigation by way of base case, upside and downside |  |  |
| NHSE dedicated support (team) |  |  |  |  |  |  | System Exec oversight |  |  |
| Triple lock now in place. |  |  |  |  |  |  | System DoF meeting |  |  |
| Case for Change endorsed by region and signed off by ICS Execs |  |  |  |  | tbc |  | System Improvement Assurance Group |  |  |
| Peninsula Acute Sustainability Programme Plan to April 2023 |  |  |  |  | tbc |  | SoF Metrics included within IQPR |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |
| NHSE recovery plan sign off. |  |  |  |  |  |  | ICB missing key performance targets |  |  |
| UEC Strategy. |  |  |  |  |  |  | SOF4 |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| Risk assessment underway to agree the proposed final forecast position and whether the ICB can deliver the agreed Operational Planning position. |  |  |  |  |  |  |  |  | Tbc |
| Set appropriate level of CIP |  |  |  |  |  |  |  |  | Tbc |
| Develop a capital programme that aligns and supports delivery of the operational plan/to include technology advancements/digital agenda etc |  |  |  |  |  |  |  |  | Tbc |  |
| ICS Infrastructure Strategy |  |  |  |  |  |  |  |  | December 2023 |  |

| Make more efficient use of our resources Corporate Objective: (10) Develop a workforce strategy to ensure resilience of key services |  |  |  |  |  | Director Lead: Paul Renshaw |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk If the ICB does not produce an agreed system wide workforce strategy that meets the health and care needs of the population, is affordable and can be delivered by system partners, then it will continue to have high costs and be unable to ensure resilient, safe, and effective services. As a consequence the ICB will continue to fail to meet statutory constitutional targets. |  |  |  |  |  | Principal Assurance Committee: People and Culture Committee |  |  |
|  |  |  |  |  |  | Devon Challenge 8: Varied education, training, employment opportunities, workforce availability and wellbeing. ICS Strategic Goal: enhancing productivity and value for money. We will have enough people with the right skills to deliver excellent health and care in Devon, deployed in an affordable way. |  |  |
|  | Likelihood | Impact | Move | Risk Score | Target | Appetite: Open. By using our workforce differently, we are prepared to accept some short-term clinical risk. |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 | 6 |  |  |  |
| Risk score: Feb 23 | 3 | 4 |  | 12 |  |  |  |  |
| Key update on actions for February 2023 A One Devon Workforce Strategy is currently being developed. Stakeholder engagement has been undertaken with c300 executive, clinical, professional and workforce leaders across the Devon System to inform the strategy development. Draft strategy is now being consulted on with SET, Exec Workforce group and People and Culture Committee. This will go to Board members informally in March with an aim for this to be formally approved in April. |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  | In place |  | Assurances: |  |  |
| Work Force Strategy (expected formal sign off in April 23) |  |  |  |  |  | Workforce strategy steering group in place |  |  |
| 5 Year workforce plan (expected 30th June 2023) |  |  |  |  |  | People & Culture Committee to receive monthly progress highlight report of People Plan delivery pillars |  |  |
| Control Gaps |  |  |  |  |  | Assurance gaps |  |  |
| Workforce Strategy |  |  |  |  |  | Integrated workforce report and dashboard not yet in place - needed for Q1 2023, but ongoing issues with resourcing from BI being worked through. |  |  |
| Workforce and recruitment plans |  |  |  |  |  |  |  |  |
| Learning and Education Strategy |  |  |  |  |  |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  | Action Status | Planned Completion Date |
| Work force Strategy and associated 5-year workforce plan in development. |  |  |  |  |  |  |  | Strategy due to be signed off April 23 by Board Workforce Plans due 30/06/23 |
| Learning & Education strategy in development |  |  |  |  |  |  |  | Planned to be completed for Q2 2023/24 |
| Accelerate the introduction of new roles and expand advanced clinical practitioners. |  |  |  |  |  |  |  | From Q2 2023/24 |

| Make more efficient use of our resources Corporate Objective: (11) Maximise the use of digital technology and data so it [care] is evidence based and outcome focused |  |  |  |  |  |  | Director Lead: Bill Shields |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk: If we fail to resource and work collaboratively towards the common priorities presented in the Digital Strategy we will not be able to maximise the benefits afforded by the advances in digital and data, including the ability to identify and tackle health inequalities. |  |  |  |  |  |  | Principal Assurance Committee: Finance Committee |  |  |  |
|  |  |  |  |  |  |  | ICS Digital vision: Invest in a digital Devon: people will only tell their story once, first contact will be digital where appropriate and more advice and help will be available online. We want to make the most of advances in digital technology to help people stay well, prevent ill-health, and provide care |  |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target |  | Risk Appetite: Seek |  |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 |  | 8 |  |  |  |  |  |
| Risk score: Feb 23 | 3 | 4 |  | 12 |  |  |  |  |  |  |  |
| Key update on actions The digital strategy and progress of delivery will be presented to the ICB in March 2023 £85m has been allocated to DPT, UHP and TSDFT to complete their digitisation journey GPIT Futures re-procurement for primary care systems to be completed in 2023 |  |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |  |
| Digital Strategy |  |  |  |  |  |  | TOPAG highlight reports |  |  |  |
| Digital Transformation Board |  |  |  |  |  |  | Reports to ICB |  |  |  |
| Single Technical Design Authority |  |  |  |  |  |  | Reports to NEMs |  |  |  |
|  |  |  |  |  |  |  | Involvement of NHSE across governance levels |  |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |  |
| Over reliance on provider digital resources who have other competing local priorities |  |  |  |  |  |  | Competing local priorities |  |  |  |
| A culture of whole system thinking across the ICS has yet to be achieved |  |  |  |  |  |  | Lack of financial resources* |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| National funding streams with a focus on digital* |  |  |  |  |  |  |  |  |  |  |
| Requests to confirm status of Digital Team member’s contracts (1x Programme Manager and 2 x Project Managers) |  |  |  |  |  |  |  |  |  |  |
| Whole system workshops held to bring ICS organisations, critical suppliers and NHSE together to progress strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| Digital Inclusion Group (membership includes VCSE) to give strategic steer on digital inclusion issues |  |  |  |  |  |  |  |  |  |  |  |  |

| Improve Services and reduce unwarranted variation Corporate Objective: (12) Minimise our negative impact on the environment and ensure services are green/sustainable. |  |  |  |  |  |  | Director Lead: Andrew Millward |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk: If the ICB does not support the co-ordination of carbon reduction across the ICS and embed the principles for Healthier Planet, Healthier People then it will not create a greener, sustainable health service in a way that contributes to the NHS Target of reaching net zero by 2040 (for emissions it controls directly and by 2045 for those it can influence (such as the supply chain). The consequence will be that we fail in our responsibilities to tackle the impact of the climate emergency on the health of the population and for future generations. |  |  |  |  |  |  | Principal Assurance Committee: Finance Committee |  |  |  |
|  |  |  |  |  |  |  | Devon Challenge: 2: Climate Change ICS Strategic Goal: We will create a greener and more environmentally sustainable health and care system in Devon, that tackles climate change, supports healthier living (including promoting physical activity and active travel). |  |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target |  | Risk Appetite: Seek |  |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 |  | 8 |  |  |  |  |  |
| Risk score: Feb 23 | 3 | 4 |  | 12 |  |  |  |  |  |  |  |
| Key update on actions NHS Devon’s Green Plan has been written with contributions from acute trust partners and general practice. This provides a framework to support the individual partner Green Plans. Clinical Green Champion now recruited. |  |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |  |
| Estates/Sustainability Lead meetings taking place |  |  |  |  |  |  | Action log produced |  |  |  |
| Clinical Green Champion |  |  |  |  |  |  | Updates to GP Collaborative Boards |  |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |  |
| Resources and capacity – no resources have been identified to support the implementation of the Green Plan. There is currently no dedicated strategic resource at an ICS level for the Green agenda |  |  |  |  |  |  | Formal governance arrangements not in place and no formal route to the ICB Board. |  |  |  |
| NHS Devon’s Green Plan does not currently have an associated delivery plan |  |  |  |  |  |  | Annual review of the Green Plan due March 2023 |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| There are potential options in place to provide a dedicated ICS resource for the Green Agenda. |  |  |  |  |  |  |  |  |  | April 2023 |
| A NHS Devon Green Plan delivery plan will be produced in line with the dedicated resource. |  |  |  |  |  |  |  |  |  | April 2023 |

| Develop our culture and how we operate Corporate Objective: (13) Develop and embed a new culture for the ‘One Devon’ system and create stronger relationships built on integration and trust. (14) Develop a system operating model, so we are clear on system decision making, local care partnership accountability and development of a more locally based, citizen led approach to planning and delivering services. |  |  |  |  |  |  | Director Lead: Simon Tapley |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk If ICB does not set clear timescales and expectations for the development of the system operating model as a result of the inertia (inactivity) caused by operational pressures, then some partners will become disengaged and unable to focus on wider system objectives. The consequence will be a break down in trust between partners, which will undermine the relationships needed to fully develop an integrated care system. |  |  |  |  |  |  | Principal Assurance Committee: ICS Executive Strategy and Transformation |  |  |
|  |  |  |  |  |  |  | ICS aim: creating an environment for success - Integrated System Development Programme. |  |  |
|  | Likelihood | Impact | Move | Risk Score |  | Target | Key update on actions for Feb/ March 2023 Intention to run a session with ICB Execs to ensure alignment ahead of wider system discussions was deferred. Session to be rearranged. Work on the ‘Development and Delegation Framework’ will continue. |  |  |
| Inherent Risk Score | 4 | 4 | No change | 16 |  | 6 |  |  |  |
| Risk score: Feb 23 | 4 | 4 |  | 16 |  |  |  |  |  |
| Appetite: Seek Eager to be innovative and to choose options offering higher business rewards. |  |  |  |  |  |  |  |  |  |
| Key Controls: |  |  |  |  | In place |  | Assurances: |  |  |
| Op Model Implementation meetings with senior leadership from across the ICB and system partners meeting monthly |  |  |  |  |  |  | Board approval on Devon Operating Model |  |  |
| Peninsula Acute Sustainability Programme agreed in principle with lead provider |  |  |  |  |  |  | ICS maturity assessment |  |  |
| Control Gaps |  |  |  |  |  |  | Assurance gaps |  |  |
| Delay ICB Exec agreement of vision and timescales for implementation |  |  |  |  |  |  | Operational pressures 2022-23 ongoing impacting ability to move forward with delegation framework. |  |  |
| Development and Delegation Framework |  |  |  |  |  |  |  |  |  |
| Plan and timeline for adoption of additional responsibilities |  |  |  |  |  |  |  |  |  |
| Mitigating Actions: |  |  |  |  |  |  |  | Action Status | Planned Completion Date |
| ICB to establish delegation framework to include: governance (formally approved ToRs, membership, reporting etc); assessment of capacity and capability (including that provided by transfer of staff to new body). May use elements of the ICS Maturity Assessment. |  |  |  |  |  |  |  |  | tbc |
| Provider Collaboratives and LCPs (alongside ICB) to assess fitness to deliver current responsibilities as described (ToRs, membership, workplans etc). Majority of responsibilities already understood and accepted but may be waiting for formal notification to proceed. |  |  |  |  |  |  |  |  | tbc |

Annex B Scoring methodology.

The inherent risk score is the rating assigned to a risk before any mitigations/controls are applied; the current risk score is the rating assigned to a risk that takes account of the mitigations/controls applied to it.

Good Governance Institutes Framework definitions:

END OF DOCUMENT