# Reducing & Mitigating Against Health Inequalities in Planned Care

Dr Claire Hooper, Strategic Clinical Lead for Planned Care in Devon

Dr Helena Posnett, Consultant in Public Health (Health Inequalities)

ICB Board for Devon

18 January 2022

Table of Contents

1	What are Health Inequalities?	3

1.1	Introduction	3

1.2	What is the evidence of Health Inequalities in Planned Care?	4

1.2.1	Pre-Pandemic	4

1.2.2	Recovery	4

2	What the Devon system is doing to reduce Health Inequalities in Planned Care	5

2.1	Operations Planning process for 2022/23	5

2.2	Why have systems and trusts been asked to do this?	5

3	Health Inequalities work plan for Planned Care	6

3.1	Assessment of progress	6

3.1.1	Progress against work plan for Planned Care	6

3.1.2	Assessment of progress from the trusts	10

3.1.3	Planned Care Programme Board, November 2022	10

3.2	Next steps	12

# What are Health Inequalities?

## Introduction

Health inequalities are systematic, avoidable, and unjust differences in health and wellbeing between different groups of people. There is clear evidence that reducing Health Inequalities improves life expectancy and reduces disability across the social gradient. Tackling Health Inequalities is therefore a core part of improving access to services, quality of services, and health outcomes for the whole population.

Health Inequalities are ultimately about differences in the status of people’s health. But the term is also used to refer to differences in the care that people receive and the opportunities that they have to lead healthy lives – both of which can contribute to their health status. Health Inequalities can therefore involve differences in:

- health status, for example, life expectancy,

- access to care, for example, availability of given services,

- quality and experience of care, for example, levels of patient satisfaction,

- behavioural risks to health, for example, smoking rates,

- wider determinants of health, for example, quality of housing.

This means that when we talk about ‘health inequality’, it is useful to be clear on which measure is unequally distributed, and between which people.

Health Inequalities in England exist across a range of dimensions or characteristics, including the nine protected characteristics in the Equality Act (1): socioeconomic position, occupation, geographic deprivation and membership of a vulnerable group. As shown in the diagram below, these dimensions overlap, compounding the impact on persons affected.

(1) The 9 protected characteristics in the Equality Act 2010 are: age, disability, gender reassignment, marriage and civil partnership, pregnancy and maternity, race, religion or belief, sex, and sexual orientation.

Access to services refers to the availability of services that are timely, appropriate, easy to get to and use, and sensitive to user choice and need. Inequitable access can result in particular groups receiving less care relative to their needs, or more inappropriate or sub-optimal care, than others, which often leads to poorer experiences, outcomes and health status. Access to the full range of services that can have an impact on health includes access to preventive interventions and those which enable self-management, and social services; as well as primary, community, and secondary health care; and includes those delivered by voluntary, community and social enterprise sector partners, both formal and informal

Inequitable access might mean that a group faces particular barriers to getting the services they need, such as real or anticipated discrimination or challenges around language. It can mean that information is not communicated in an easily understandable or culturally sensitive way.

Sources: The King’s Fund www.kingsfund.org.uk/publications/what-are-health-inequalities;

Health Equity Assessment Tool (HEAT): executive summary - GOV.UK (www.gov.uk)

## What is the evidence of Health Inequalities in Planned Care?

Tackling inequalities in health is a long-standing NHS policy objective. Variation in the experiences and outcomes of different communities during the COVID-19 Pandemic served to bring this issue back into focus.

### Pre-Pandemic

Health Inequalities existed pre-COVID-19 Pandemic, with the Pandemic worsening this. Pre-Pandemic, persons from more deprived areas were accessing Planned Care less, and at risk of presenting late with more complex conditions. There is also evidence that decreased rates of planned care amongst lower socio-economic groups is associated with a rise in Emergency Department attendances. NHS Digital published hospital activity data in September 2020 which highlighted that during 2019/20 the most deprived decile had 7% fewer admissions for elective procedures but 51% more emergency hospital admissions than the least deprived.

Source: Socio-economic inequalities in access to planned hospital care: causes and consequences | The Strategy Unit (strategyunitwm.nhs.uk)

### Recovery

The Pandemic has highlighted and worsened existing inequities in elective care both in terms of access, outcomes and experience of people when on waiting lists. Research has shown that the growing backlog has not been experienced equally by patients and has only further exacerbated Health Inequalities faced, including likely impacting those already at risk of worse health outcomes and facing difficulties in accessing healthcare.

For instance:

- The elective recovery backlog has not grown equally across the country. Devon has experienced a c. 65% increase in elective referral waiting lists between April 2020 and July 2021, in excess of the c. 42% increase nationally.

- On average waiting lists have increased by 55.2% in the most deprived areas in England, compared to 36% in least deprived areas.

Source: NHS England

The Pandemic has placed considerable strain on planned service delivery, which was already under pressure. Consequently, there are now significant waiting lists across the country with potentially more patients still to come forward, alongside a system focus on reducing these backlogs to meet the challenging targets regarding long waits that have been set.

If Health Inequalities is looked at in relation to elective/planned care recovery since the Pandemic, specific concerns include:

- Missing referrals – who is not on the waiting lists who we would expect to be?

- Digital exclusion – who cannot access virtual appointments?

- Clinical validation favours the educated.

- Treatment offers further from home may exclude:

  - Those on lower incomes and / or in rural areas (transport access).

  - Those with more complex conditions (more likely to live in deprived areas.

Source: Socio-economic inequalities in access to planned hospital care: causes and consequences | The Strategy Unit (strategyunitwm.nhs.uk)

Failure to consider Health Inequalities in elective recovery plans risks harm to those most in need, widening of pre-existing inequalities, and individuals seeking help late leading to a worse prognosis and increased pressure on health and care services.

# What the Devon system is doing to reduce Health Inequalities in Planned Care

Given the importance of tackling Health Inequalities for our population and the importance of tackling the elective recovery waiting list, Devon continues to have a focus to ensure Health Inequalities are incorporated in the planning activities.

## Operations Planning process for 2022/23

As part of the Operations Planning process for 2022/23, NHSE has asked systems to undertake specific work relating to Health Inequalities. This includes the following requirements:

- Complete and publish an Equality and Health Inequalities Impact Assessment (EHIA) or provide a date when this will be published by, for elective recovery plans locally i.e., in Devon.

- Publish Board papers (ICSs and trusts) including analysis of waiting times disaggregated by ethnicity and deprivation, or provide a date when these will be published by:

  - Use waiting list data (pre & during Pandemic), including clinically prioritised cohorts, to identify disparities in relation to the bottom 20% by Index of Multiple Deprivation (IMD) and Black and minority ethnic (BME) populations.

  - Prioritise service delivery by taking account of the bottom 20% by IMD and BME for patients on and not on waiting list, including through proactive case finding.

  - Use system performance frameworks to measure access, experience and outcomes for BME populations and those in bottom 20% of IMD scores.

  - Evaluate the impact of elective recovery plans on addressing pre-Pandemic and Pandemic related disparities in waiting lists, including for clinically prioritised cohorts.

  - Demonstrate how the ICS’s responsible officer for Health Inequalities will work with the board and partner organisations to use local population data to identify the needs of communities experiencing inequalities in access, experience and outcomes, and ensure performance reporting allows monitoring of progress to address.

- Ensure an ongoing commitment to the validation process and prioritisation programme. This includes taking the person and wider determinants of health into account.

## Why have systems and trusts been asked to do this?

Concerted, systematic and sustained action is needed to address the multiple and overlapping web of factors that drive Health Inequalities – from differences in experiences and quality of healthcare through to the wider determinants of health. This includes, but goes well beyond, the health and care system.

Addressing Health Inequalities remains a key element of elective recovery and the Ops Planning 2022/23 submissions to NHSE required additional narrative detail on how system plans will ensure inclusive recovery and reduced Health Inequalities where they are identified. This emphasises the importance of this work.

# Health Inequalities work plan for Planned Care

## Assessment of progress

In Devon to ensure that planned care plans enable inclusive recovery, and reduce Health Inequalities where they are identified, we aim to embed a focus on Health Inequalities within all workstreams and actions to ensure that there is a focus on equity of outcomes in all the work we do. We aim to create an environment where action on Health Inequalities is seen as business as usual rather than an additional workstream, by embedding into all job descriptions and plans, workstreams and project plans.

As part of the planning process, the ICS has developed a Health Inequalities and Prevention Programme of work to further progress the Health Inequalities agenda and reduce the inequalities gap.

### Progress against work plan for Planned Care

Details of the key Health Inequalities actions in the Planned Care work plan can be seen below. This covers the action, output(s) and benefits. Progress against each of these actions can be seen in the table on the following pages.

To support this work programme, best practice examples are being sought to ensure learning from elsewhere.

| Action | Output | Benefit | RAG Rating & Comment(s) |
| --- | --- | --- | --- |
| An Equality and Health Inequalities Impact Assessment for the system elective recovery plan has been completed and has been / will be published MUST-DO | A completed NHSEI template to highlight the beneficial and detrimental impacts of Devon’s elective recovery programme on persons at risk of experiencing Health Inequalities e.g., those in protected characteristic groups and/or inclusion health groups (persons who are homeless or from the Gypsy, Roma or Traveller community) – and the mitigations in place and/or required to be implemented by the Devon System | Assurance that Devon’s elective recovery does not inadvertently widen Health Inequalities and/or where risks exist, mitigations are in place and/or planned for, and being monitored | In progress, first draft due end Dec, which will include a SMART action plan |
| The ICS will ensure board papers are published that include an analysis of waiting times disaggregated by ethnicity and deprivation MUST-DO | Published intelligence in relation to waiting lists, disaggregated by IMD and ethnicity and other priority factors** with actions plans in place including in relation to improving data quality and completeness (e.g. ethnicity coding) and other elements from https://www.england.nhs.uk/wp-content/uploads/2021/12/B1269-elective-recovery-planning-supporting-guidance.pdf: - Use waiting list data (pre & during Pandemic), including clinically prioritised cohorts, to identify disparities in relation to the bottom 20% by Index of Multiple Deprivation (IMD) and Black and minority ethnic (BME) populations. - Prioritise service delivery by taking account of the bottom 20% by IMD and BME for patients on and not on waiting list, including through proactive case finding. - Use system performance frameworks to measure access, experience and outcomes for BME populations and those in bottom 20% of IMD scores. - Evaluate the impact of elective recovery plans on addressing pre-Pandemic and Pandemic related disparities in waiting lists, including for clinically prioritised cohorts - Demonstrate how the ICS’s responsible officer for Health Inequalities will work with the board and partner organisations to use local population data to identify the needs of communities experiencing inequalities in access, experience and outcomes, and ensure performance reporting allows monitoring of progress to address ** for example, age, sex, other protected characteristics, Core20PLUS5, area of residence, rurality. | Assurance that inequalities in relation to access to waiting lists are understood, action plans are in place to address, and progress is being monitored | Sitrep sent to trusts, the results of which can be seen in Section 3.1.2, UHP has made this data available; RDUH and TSD to make available by the end of the financial year Action plans can be developed once this information is available across the system |
| The ICS and its acute providers will actively engage with the clinical validation and prioritisation programme including taking the person and wider determinants of health into account MUST DO | Agreed processes by which the person and wider determinants of health should be taken into account in the validation process. Consideration of the use of tools which take the person and their wider determinants of health into account when prioritising waiting lists e.g., HEARRT tool. All patients who are on long waiting lists are offered support to remain well while waiting. | Assurance that the validation process does not disadvantage certain groups. Assurance that prioritisation processes take the whole person into account when determining clinical need and therefore reflecting overall health need, reducing impact on other services and narrowing the historical gap in inequalities. Assurance that the Devon system is supporting long waiting patients in terms of wellbeing, information and maintaining fitness for surgery while waiting. | Need system agreement of process, including prioritisation |
| Incorporation of consideration of population needs and possible Health Inequalities at an early stage into business/service case development – NHS Devon and Trust level (NHSEI Health Inequalities feedback received) SHOULD-DO | Agreed processes to ensure Health Inequalities are taken into account early in business case and service development | Assurance that business case processes are fit for purpose and meet Devon System and NHSEI needs | In progress - to ensure is part of the process we automatically do at the beginning (Heat tool) |
| Reaching those that validation process cannot (clinical and non-clinical validation) SHOULD-DO | - Develop a process to follow up persons who are unable for whatever reason to engage in the existing non clinical validation process (telephone and online based), in order to: - Identify barriers to engagement - Implement solutions as required, including reasonable adjustments to enable person-centred offer and monitor impact | Assurance that the current non-clinical validation process is able to deliver person-centred care including reasonable adjustments, and plans are in place to monitor. | Nil currently. Work needed to understand those validation process cannot reach in clinical and non-clinical validation process |
| Missing referrals – who is not on the waiting list who should be SHOULD-DO | - Identify priority pathways where referral rates have not recovered post Pandemic - Complete equity analysis to identify areas of unmet need (for example in relation to deprivation and ethnicity) - Co-develop solutions to engage with communities to encourage presentation and early diagnosis, and monitor impact | Assurance that a plan is in place to proactively encourage engagement with services where gaps are identified, and mitigate against individuals seeking help late leading to a worse prognosis and increased pressure on health and care services, and plans are in place to monitor | Nil currently |
| Reduce impact of digital exclusion in outpatient transformation SHOULD-DO | There are clear processes in place to ensure that virtual consultations are offered when clinically appropriate and take into account a person’s needs based on their wider determinants of health. | Assurance that digital transformation of outpatient services does not increase barriers to healthcare. | Information gathering from trusts as part of OP work around offer of virtual consultations and implementation of recommendations in NHSEI EHIA |

### Assessment of progress from the trusts

A ‘sitrep’ from trusts was sought to provide oversight of progress against the information below and a RAG rating (Red, Amber and Green) assigned against each.

UHP has had additional external support from Optum, which has enabled them to be in a stronger position than the other trusts. Their support specifically focused on population health and Health Inequalities.

### Planned Care Programme Board, November 2022

Progress against the actions has unfortunately slipped due to capacity issues. As a result, the ICS Planned Care Programme Board focused on this as part of their 29 November meeting, to further push this agenda forward. The Board also considered the sitrep information from the trusts as part of this.

The Planned Care Programme Board was requested to:

- Identify a named person responsible in each provider.

- Participate [the above people] in a ‘Task & Finish’ group to develop and oversee the delivery of a workplan, share learning and monitoring of progress:

  - Ensure delivery of Health Inequalities deliverables.

  - Use data to improve access, experiences and outcomes in groups identified as having inequalities.

  - Ensure publication of board papers.

  - Provide shape to and oversight of non-clinical / clinical validation process and prioritisation and report back.

  - Ensure Health Inequalities is considered early on in the business case / service development process.

  - Robust data recording – linked to Strategic Intelligence, Evidence and Outcomes Group workplan.

  - Other priorities as agreed e.g., understanding drivers of Did Not Attend (DNAs), missing referrals, understanding those not reached by validation processes.

Providers: It was agreed that each of the providers would allocate a person responsible for Health Inequalities. At the time of writing this paper we are waiting for the name of the RDUH lead.

- TSD – Paul Procter is their contact regarding reporting. However, due to movement in the Executive Team, they are currently confirming the strategic Health Inequality Lead and will confirm who this is in due course

- UHP – Mike Hollow.

Task & Finish Group: meeting will be set up with these individuals and the system, including Public Health and Health Inequalities system leads to push this agenda forward. This will happen in January 2023.

Waiting lists data by ethnicity and deprivation: It was agreed that the two trusts who have not yet published waiting lists data by ethnicity and deprivation (RDUH and TSD) will do this by the end of the financial year. Following this, the system and providers can agree what is done as a result of having this information to push this agenda forward. We will engage with Devon’s Intelligence Functions Group to review the UHP waiting lists and data quality report and support RDUH/TSD analysis as required.

Areas of Focus: The Planned Care Programme Board is in agreement that it would be more beneficial to focus on a couple of high priority areas, where a real difference can be made to narrow the Health Inequalities gap. Given the context with the operational challenges the system continues to have, including the increased scrutiny by NHSE on long waiting patients, this was felt to be a reasonable pace to take this forward. It was suggested that Orthopaedics would be a good speciality to focus on as this has our longest waiting patients.

In addition, there is an opportunity to align efforts with Devon’s approach to the CORE20+5 (England’s national health inequaliteis programme, for adults, children and young people), as follows:

- Devon’s Priority Populations (CORE20+):

  - the most deprived 20% of the national population living in Devon

  - Individuals, families and communities experiencing rural and coastal deprivation

  - Individuals, families and communities adversely affected by differential exposure to the wider determinants of health – for example, those with unstable housing or homeless, vulnerable migrants and/or those experiencing domestic abuse.

  - Persons with severe mental illness and learning disability, and autistic persons

- Areas of clinical focus aligning to Planned Care e.g. early cancer diagnosis, paediatric tooth extractions

These areas of focus will be agreed in a future Planned Care Programme Board meeting early next year.

EHIA for elective recovery: This is in the process of being produced and will identify the Health Inequalities gaps relating to planned care. The EHIA will have a SMART action plan to drive Health Inequalities across the system. The draft EHIA will be available by the end of the calendar year. The EHIA and action plan will come to the January Planned Care Programme Board, which will give consideration to and agree which specialities to focus on and the system-wide priority areas for action.

Health & Inequalities and Preventions Steering Group: in its meeting on 30 November, this Group agreed to support  trusts in identifying leadership for these roles and also be part of the working group.

Ahead of January’s Planned Care Programme Board: it was agreed that a paper relating to ‘Waiting List Scheduling Tool’ to take into account the wider determinants of health of a person would be sent. As part of this, we will consider the use of HEARTTTM (Health Equity and Referral to Treatment), which has been developed by University Hospitals Coventry and Warwickshire NHS Trust (UHCW). In 2020, University Hospitals Coventry and Warwickshire NHS Trust (UHCW) analysed their waiting lists and found that their most deprived patients had a longer average wait than the least deprived. To address this, they developed a software tool (HEARTT) to assign a weighting to patients that impacted their waiting list position.

It is worth noting that there is ongoing work programme of work, covered in section 3.1.1 earlier in this report, to progress this work.

## Next steps

The next steps for the Devon system have been summarised below:

- Complete draft EHIA and SMART action plan – end December 2022.

- EHIA and SMART action plan to Planned Care Programme Board – 19 January 2023.

- Task & Finish Group meeting – January 2023.

- Send the ‘Waiting List Scheduling tool’ paper to Planned Care Programme Board ahead of the 19 January meeting.

- Agreement regarding the high priority areas of focus for Health Inequalities and planned care – early 2023 (date TBC).

- Engagement with Devon’s Intelligence Functions Group to review the UHP waiting list and data quality report and support RDUH/TSD analysis as required.

- RDUH and TSD to publish waiting list data by ethnicity and deprivation – end March 2023.

- Agree what actions can be taken as a result of providers having made their waiting lists data available by ethnicity and deprivation – date TBC.

- Continuation of Health Inequalities programme of work – ongoing.